## Sheet1
YRITWC's Communities Listed in Contaminated Sites | Location | Latitude/Longitude | Primary Type of Contamination | Other Contaminants Present | Quantity | Area | Date Identified | Status of Clean Up | Updates
Alakanuk
Bone Yard | 5th st | 62.68750000, 164.6683333 | Old equipment | Vechiles, tanks, tires | 51 items dumbed | 2.5 acres | 2020-10-01 | Active | 7/11/2022- The site was visited by YRITWC staff. Updating coordinates to have the correct ones on file. Also got areal photos. Working on getting the eligibility form for the site and Phase I will be coming up with the summer of 2023
Native Store | Mouth of Alakanuk | ---------------------------------------- | Abondoned | fuel | 7 building | 1 acres | 2020-10-01 | Active | 10/2020 Added into inventory 7/11/2022 Updated photos taken of site
Old BIA School North Bank | Alakanuk Slough, on North bank | ---------------------------------------- | Abondoned | asbestos, lead paint, waste from honey buckets | 1 building | 1 acre | 2006-07-12 | Cleaned up | 10/28/2022 YRITWC was informed that this site has been cleaned up
Arctic Village
Old Generator Building | Along the side of the airport landing strip | ---------------------------------------- | Abondoned | Fuel, batteries, old machinary, | 100 drums, 5 batteries, 10 vehicles, 1 building | 2 acres | 2007-05-04 | Active | 7/28/2022 Aerial photos were taken. Talks of potentially getting a phase I of site
Public Health Service Building | Middle of village | ---------------------------------------- | Abondoned | fuel, chlorine, and fluoride | 1 building | 50ft x 20ft | 2007-05-04 | Active | 7/28/2022 updated photos were taken of site
Washeteria Tank | Next to the school | ---------------------------------------- | Fuel Spill | Fuel | 1 tank | 15ft x 15ft | 2007-05-04 | Active | 7/28/2022 updated photos
Beaver
BIA School | 400 C street | ---------------------------------------- | Abondoned | Abestos, Lead, Petroleum | 1 building |  | 2007-05-01 | Active | 8/2022 Limited Hazardous Building Materials Inventory was done
Birch Creek
DOT Shop | Adjacent to runway & lake | --------------------------------------- | fuel |  | tanks | 1 acre | 2008-06-05 | Active | Listed as an upcoming village visit 2023
Dump | South west end of town | --------------------------------------- | Dump | house hold waste |  | 3 acres | 2008-06-05 | Active | Listed as an upcoming village visit 2023
Power Plant | Airport | ---------------------------------------- | Petroleum | fuel |  | 1 acres | 2008-06-05 | Active | Listed as an upcoming village visit 2023
School Tank | Middle of Community | ---------------------------------------- | Petroleum | Diseal | 3 generators, 1 backup generator | 50 ft x 100 ft | 2008-06-05 | Active | Listed as an upcoming village visit 2023
Chevak
Old Lagoon/ Lake/ Dumpsite |  | 61.525972927, -165.586611616 | Sewage | Soild waste | unknown | 330 ft x 300 ft | 2006-07-11 | Active | Listed as an upcoming village visit 2023
Old School Building |  | 61.528185596,-165.586272560 | Abandoned | Diesel | unknown | 300ft x 300ft | 2006-07-11 | Active | Listed as an upcoming village visit 2023
Old School Tank Farm |  | 61.528512330 -165.587517946 | Diesel |  | unknown | unknown | 2006-07-11 | Active | Listed as an upcoming village visit 2023
Wastewater Plant/ Tank Farm |  | 61.527485657 -165.589519152 | Diesel |  | unknown | unknown | 2006-07-11 | Active | Listed as an upcoming village visit 2023
Fort Yukon
School |  | ---------------------------------------- | Petroleum | Diesel | Unknown | unknown | 2008-06-04 | Active | Listed as an upcoming village visit 2023
Old Landfill |  | ---------------------------------------- | solid waste |  | unknown | 10 acres | 2008-06-04 | Active | Listed as an upcoming village visit 2023
Crowley Tank Farm |  | ---------------------------------------- | Petroleum |  | unknown | 2acres | 2008-06-04 | Active | Listed as an upcoming village visit 2023
BLM Fuel Storage |  | ---------------------------------------- | Petroleum |  | unknown | 50ftx50ft | 2008-06-04 | Active | Listed as an upcoming village visit 2023
Galena
High School |  | ---------------------------------------- | Petroleum |  | unknown |  | 2007-05-22 | Active | Listed as an upcoming village Visit 2023
Fish Plant |  | ---------------------------------------- | Petroleum | Diesel |  |  | 2014-05-05 | Active | Listed as an upcoming village Visit 2023
Grayling
Native Store USTs | North Side of "C" Street, Between 2nd & 3rd Streets | 62.905015, -160.065396. | Petroleum | Gasoline, Diesel | unknown | 1 acre |  | Active | 9/27/2022 - visted Grayling to get a history of site10/27/2022 Eligbility form complete. Plans of phase II on site
Hughes
School Tank Farm | 110 Front Street | 66.045785, -154.259010 | fuel | Gasoline | unknown | unknown |  | Active | 1/19/2023 A phone meeting was called about moving forward on site. Phase I being planned for the summer
Huslia
old Barge site |  | 65.693462,-156.387164 | oil | Vehicles | unknon | 3.5 acres |  | Active | 7/18/2022- Visited the site and got updated photos and samples of drums. Started eligibility forms for this site. Phase I planned
Koyukuk
Koyukuk City Bulk Fuel Storage | Across from School | -------------------------------------- | Petroleum |  | Unknown | Uknown | 2007-05-21 | Active | Listed as an upcoming village visit 2023
Koyukuk Pipe Spill | Next to School | -------------------------------------- | Petroleum |  | Unknown | Uknown | 2007-05-21 | Active | Listed as an upcoming village visit 2023
Koyukuk Sewage Lagoon | Behind washeteria, next to YKSD Bulk fuel storage facility | ---------------------------------------- | Sewage |  | Unknown | Uknown | 2007-05-01 | Active | Listed as an upcoming village visit 2023
Koyukuk Washeteria Pipe | Behind Washeteria | ------------------------------------- | Petroleum | Human Waste | Unknown | Uknown | 2007-05-01 | Active | Listed as an upcoming village visit 2023
Koyukuk YSKD Bulk Fuel Facility | Behind School | -------------------------------------- | Petroleum |  | Unknown | Uknown | 2007-05-01 | Active | Listed as an upcoming village visit 2023
Northway
Northway ACS/ DERP | Alaska Highway, Northway Junction, Northway, AK 99764 | 63.013014, -141.805349 | Petroleum | Heavy Metal Contamination, solvent | Unkown | Unknown |  | Active | Listed as an upcoming village visit 2023
Northway Staging Field OU2, Areas 40&43-Ham Lake | Sites 40 and 43, Ham Lake, Northway, AK 99764 | 62.964624, -141.918537 | Petroleum | DRO | Unkown | Unknown |  | Active | Listed as an upcoming village visit 2023
Rampart
Rampart School | Tracts 2A/2B of USS3677, Rampart, AK 99767 | 65.504990, -150.169990 | Oil |  | 2000 gallon | Unknown | 2009-04-01 | Active | Listed as an upcoming village visit 2023
Rampart Tanker Rollover Airport Road | Airport Road; Lot 1 Block 2 USS 5049, Rampart, AK 99767 | 65.509017, -150.159167 | Diesel | gasoline | 4000 gallons | Unknown | 2013-04-11 | Active | Listed as an upcoming village visit 2023
St. Mary's
Yukon Traders old store | 2 adjacent lots in town | ------------------------------------- | GRO | Depri | unknown | Unknown | 2022-09-26 | Active | 9/26/2022- Email exchanges have been made about the site and it has been added to our inventory and will work on-site assessments with in coming years
St. Michaels
Saint Michaels Former Airstrip | Old Airport Way, Saint Michael, AK 99659 | 63.482500, -162.030300 | DRO | RRO | Unknown | Uknown | 1999-07-01 | Active | Listed as an upcoming village visit 2023
Bakery | Near Catholic Church | ------------------------------------ | Potentally lead paint | Potentally Asbestos | Unknown | 10m | 2006-08-01 | Active | listed as an upcoming village visit 2023
BSSD Tank Farm | Barracks Steet | ------------------------------------ | Fuel |  | Unknown | 100 ft sq | 2006-05-01 | Active | listed as an upcoming village visit 2023
Drum Fill Road | Runs Behind AC store across Airport road to Old airstrip | ------------------------------------- | Fuel |  | Unknown | Unknown | 2006-05-01 | Active | listed as an upcoming village visit 2023
Straight Arrow Building | NE of Commissary, SW of AVEC fuel storage tanks | -------------------------------------- | Potentally lead paint | Debris | unknown | 100 ft sq approx. | 2006-08-01 | Active | listed as an upcoming village visit 2023
Former AC Gas Station / Tar Pit | 255 Main Street | ------------------------------------ | Fuel | Tar pit | unknown | 70 ft x 40ft | 2006-05-01 | Active | listed as an upcoming village visit 2023
Stebbins
AVEC Tank Farm | Terminal St. & Southern St. | ------------------------------------- | Fuel |  | unknonw | uknown | 2006-05-01 | Active | listed as an upcoming village visit 2023
Spill Near School | Near Boat Storage Area | ------------------------------------- | Fuel |  | unknown | 3/4 Acres | 2006-05-01 | Active | listed as an upcoming village visit 2023
Former Fuel Pump House | Along bank of Norton Sound | 63.521720860, -162.290120363 | Fuel |  | Unknown | 50 -100 ft | 2006-05-01 | Active | listed as an upcoming village visit 2023
Tanacross
Old BIA School | Lot 5 Block 5 of USS 3726 Townsite | N 63.83, W 143.54 | Potenally Lead | Potenally Asbesots | Unknown | 1.6 acres | 2006-08-01 | Active | listed as an upcoming village visit 2023
Venetie
Venetie Current Dump | Near the end of the old aiport | -------------------------------------- | Soild waste | White products | unknown | 4 Acres | 2007-05-01 | Active | 7/26/2022- Staff visited site and got updated photos, and asked if there is any resue plan for the future.
Venetie Old BIA School | By new school and city office | ------------------------------------- | Potentally Lead | Potentally Asbestos | Unknown | 30 ft x 30ft | 2007-05-01 | Active | 7/26/2022- Staff visited the site and got updated photos, and asked if there is any rescue plan for the future. Have talked about potentially starting working on site HBMI
Venetie Old Generator House | Along airport strip | ------------------------------------- | Soild waste | Fuel | Unknown | 30ft x 30ft | 2007-05-01 | Active | 7/26/2022- Staff visited site and got updated photos, and asked if there is any resue plan for the future.
Venetie Old Sewage Lagoon | Next to Washeteria | ------------------------------------- | Sewage |  | Unknown | 35ft x 35ft | 2007-05-01 | Active | 7/26/2022- Staff visited site and got updated photos, and asked if there is any resue plan for the future.
Venetie Recycling Center | Located in middle of village. | ------------------------------------- | Petroleum | Batteries | Unknown | Unknown | 2007-05-01 | Active | 7/26/2022- Staff visited site and got updated photos, and asked if there is any resue plan for the future.